## Sheet1
Sprint / Phase | Task ID | Task Name (Feature / Task) | Status | Completion Date (Log Date) | Commit Message (GitHub Evidence)
SPRINT 1-3 | INIT | Foundation, Auth & Expense Core | Done | 13/11/2025
(Week 1) | BE-01 | Project Initialization & Folder Structure | Done | 13/11 | init: initial project setup
| BE-02 | Handle Login/Register & Profile Logic | Done | 13/11 | feat: complete sprint2 - auth flow...
| FE-01 | Expense CRUD Functionality (Add/Edit/Delete) | Done | 13/11 | feat: complete sprint3 - full CRUD...
SPRINT 4 | BDG | Budget Management & Dashboard | Done | 15/11/2025
(Week 1) | BE-03 | Budget Management Logic & Reporting | Done | 15/11 | feat: complete sprint4 - budget...
| FE-02 | Dashboard Display Integration | Done | 15/11 | feat: complete sprint4 - ... dashboard
SPRINT 5 | ADV | Recurring & Income | Done | 17/11/2025
(Week 2) | BE-04 | Handle Recurring Expenses & Income | Done | 17/11 | feat: complete sprint5 - recurring...
| FE-03 | Quick Edit Feature & Multi-currency Support | Done | 17/11 | feat: complete sprint5... quick edit...
| QA-01 | Fix Sprint 5 Logic Bugs | Done | 18/11 | fix sprint 5, Hoan thanh Sprint 5...
SPRINT 6 | UI | UI Polish & Overview | Done | 18/11/2025
(Week 2) | FE-04 | Polish Overview UI Layout | Done | 18/11 | Sprint 6 Overview
SPRINT 7 | FIN | Report, Feedback & Finalize | Done | 18/11/2025
(Week 2) | BE-05 | Report & Feedback Module Implementation | Done | 18/11 | Hoan thanh Sprint 7 Report & Feedback
| BE-06 | Update Recurring Expense Logic | Done | 18/11 | Hoàn thiện 'Recurring Expenses & Income'
MAINTENANCE | FIX | Bug Fixing & Optimization | Done | 19/11 - 24/11
(Post-Sprint) | QA-02 | Fix Login Bugs & General Logic | Done | 19/11 | fix lg, Merge remote-tracking...
| QA-03 | Fix Biometric Security Bugs | Done | 20/11 | fix vantay
| QA-04 | Fix Localization Bugs (Multi-language) | Done | 21/11 - 23/11 | fix language1, fix language3
| QA-05 | Update Forgot Password Feature | Done | 24/11 | update ForgotPassword
RELEASE | DOC | Final UI & Documentation | Done | 25/11 - 26/11
(Final) | FE-05 | Update UI (Main, Budget, Report Screens) | Done | 25/11 | update main and login, update budget
| FE-06 | Fix Navigation Bar & Avatar Display | Done | 25/11 | fix thanh dieu huong, update spiner...
| DOC-01 | Draft & Upload User Guide PDF | Done | 26/11 | Add User Guide PDF, Add files...
| DOC-02 | Cleanup Old Documentation Files | Done | 26/11 | Delete Technical Documentation .pdf
Note on Sprint Timeline: "Due to the highly concentrated implementation phase (Nov 13 - Nov 26), the team adopted a 'Fast-tracking' strategy. Sprints 1-3 were merged to accelerate the Foundation phase, ensuring the core architecture was ready immediately. Sprints 4-7 were then broken down into granular daily milestones to strictly control advanced feature implementation. The final Maintenance phase was dedicated entirely to Bug Fixing and Documentation to ensure stability for the release."